## Test_description
Test ID	Goal	Description	Detailed Decription	Analysis	Outcome	Number of orbits required	Time required for analysis (days)	Success criterion	Day of comissioning	Manual guidance needed	Expected total data	Expected data per orbit	Comment
Alignment_test_1	Establish exact alignment via star calibrations	Do star calibration for a few orbits, looking with star in center and +- 50 % FoV in each direction.	?	1. Compare estimated position of start with observed position for each channel. / 2. Update rotation matrices. / 3. Check imaging PSF reasonable	Updated rotation matrices for correct alignment. / Updated PSF estimate.	30	2	Star found	4	Yes	61MB	2MB	Star calibration
Limb_functional_test	Establish that imaging provides a reasonable signal and that pointing (vertical) is correct within 1 degree. IR3 or IR4 will be used as reference.	Test compressed images by performing snapshots with one and one channel at different limb altitudes and different integration times. To be done over nighttime and daytime earth.	0. Set payload to idle mode. / 1. Set all CCDs except Nadir to FullReadout, 1s integration time / 2. Point at 50 km / 3. Take one snapshot with each CCD one at a time with 5 s between each command / 4. Redo images with integration time of 2,4,8,16 s / 5. Redo with BinnedCalibration (but snapshots one at a time) / 4. Redo images at 70, 90, 110, 130, 160 and 200 km	1. Visually inspect images. / 2. Compare to Sasktran simulations and establish first estimate throughput of system (limb radance → counts) / 3. Compare to Sasktran and establish first estimate pointing error / 4. Use signal at 160 and 200 km at nighttime to estimate dark current, bias. / 5. Use signal at daytime to estimate straylight / 6. Compare compressed and uncompressed images to check consistency.	An initial set of CCD parameters to use for the rest of the comissioning activites.	7-9	2-4	Visual analysis ok for both uncompressed and compressed images. / Radiometric calibration within 50 % of pre-flight estimation	1		500 MB (TBC)	~100 MB	Reduce to 1 day. Check avalible storage in MM. Can manouvers be executed during night?
Photometer_test_1	Show that photometer produces a reasonable signal, and establish optimal integration time.	Perform photometer measurements with of 1,2,4,8,16 s exposure time. Alternating across the orbit for one orbit. (2 min intervals) daytime		1. Check that results scale linear with integration time. / 2. Compare results to sasktran and compare pre-flight estimates.	Photometer integration time	1-2	1	linearity ok.	1		<1MB		Check with operational mode?
Nadir_functional_test	Show that Nadir imaging is reasonable and establish ideal integration time	Test compressed images by performing snapshots with different integration times. To be done over nighttime and daytime earth at 30 N, 0 N and 30 S latitude nighttime/daytime	0. Set payload to idle mode. / 1. Set CCD to FullReadout images, 1s integration time / 2. Point at nominal pointing altitude. / 3. Take snapshots integration time of 1, 2,4,8,16 s	1. Visually inspect images / 2. Compare to SASKTRAN simulations. / 3. Establish initial absolute calibration values (sasktran→ measurements) and compare to pre flight estimations.	Nadir imager integration time	1	1	Visual analysis ok for both uncompressed and compressed images. / Radiometric calibration within 50 % of pre-flight estimation	1		7MB		Nighttime images limb and nadir, FF and binned (5s/1s)
Operational_image_test_1	Test instrument in operational modes. This is to test the data processing chain with realistic data, and to provide a larger data set on which to do analysis on during the first week. / This data may also provide some good oportunities for PR images.	Put instrument in mode 1 (NLC mode), based on pre-flight estimated parameters.	Run normal mode 1	1. Visually inspect every 10th image? (1000 images in total) / 2. Run through L1 processing using pre-flight estimated (without photometer correction) / 3. Compare to SASKTRAN. Compare to OSIRIS?	A calibrated dataset	14++	2	Difference between measurements and SASKTRAN simulations less than 90 %	2-3		Nominal		Fine tuning operational mode
Alignment_test_1	Establish exact alignment via star calibrations	Do star calibration for a few orbits, looking with star in center and +- 50 % FoV in each direction.	?	1. Compare estimated position of start with observed position for each channel. / 2. Update rotation matrices. / 3. Check imaging PSF reasonable	Updated rotation matrices for correct alignment. / Updated PSF estimate.	30	2	Star found	4	Yes	61MB	2MB	Star calibration
Operational_image_test_2	Test operational modes with paramteres updated from limb_functional_test	Put instrument in mode 1 (NLC mode), with updated parameters.	Run normal mode 1	1. Visually inspect every 10th image? (1000 images in total) / 2. Run through L1 processing (without photometer correction) / 3. Compare to SASKTRAN. Compare to OSIRIS?	An improved calibrated dataset	14++	1	Difference between measurements and SASKTRAN simulations less than 50 %	5-6		Nominal
Alignment_test_2	Establish alignment via looking at moon	Image moon in all channels	?	?		6	1		7	Yes	12MB	2MB
CCD_stability_test	Check if CCD parameters (Dark current and bias) varies around the orbit	Look at NP km (dark space) and take images with different integration times.	0. Set payload to idle mode. / 1. Set all CCDs except Nadir to FullReadout, 1s integration time / 2. Point at 230 km / 3. Take snapshots with CCDs one at a time with 5 s between each command / 4. Redo images with integration time of 2,4,8,16,32 s	1. Estimate dark current and bias at different part of the orbit. / 2. Compare to housekeeping data (temperatures) / 3. Analyze straylight perfomance over daytime part of orbit.	Updated calibration coefficients for the CCD.	1	1	CCD parameters stable (within 5 %) around the orbit.	8		<Nominal
Rayleight_test_1	Establish abosolute calibration of limb imager	Perform absolute calibration using rayleigh scattered light with little to no upwelling. / Shall be done when night under the satellite and day at the limb	?	1. Compare results from SASKTRAN simulations. / 2. Compare results to star calibration	updated calibration coefficient for radiometric calibration	6	1	Star and rayleigh calibration agree within 20 %	8	YES	Limb sweep

Nadir_alignment_test	Check nadir, alignment	Take picture over known geographic locations?				1	1	Location found (to what accuracy?)	9
Nadir_dark	Get dark current for nadir camera	Nadir camera should point ut into dark space? (Pitch very far?)				1	1	Dark current matches lab measurements within 10%	10	YES	Limb och nominal pointing
Limb_ground_target (?)	Look at ground target with limb imager to confirm pointing and resolution. As well as get a feeling for the instrument	Very large pitchover to look straight down.				1	1	Ground target found	10	YES
Polarisation_test_1	Check polarisation response of instrument.	Based on location determined by Rayleigh_test_1 perform a roll manouver +-45 degrees while looking at a limb altitude of 60 km		1. Compare to SASKTRAN simulations	Updated calibration coefficients for polarization compansation.	3	1	Polarisation response of UV channels is within 20% of SASKTRAN calculations (incl instrument model)	11	Yes	Binned
					Coincidence odin measurements