## Sheet1
Pass # / orbit	Day	test name	Goal	Description	Detailed Decription	Analysis	Outcome	Procedure ID	Dependency	Platform actions	number of images	size/image	Expected data in next pass)	Cumulated data (over night)
0	D-1		Heat instrument	Turn on instrument	Turn on payload, heaters and CCDs	Check if temperature has reached equilibrium	Equilibrium temperatures	-	-	-	0	-	<1MB
1	1	Star staring 1	Prove star finding capacity	Take pictures of stars with single channel	Start with limb pointing at 90 km and follow star up to 400 km? taking images with IR3 with 5s, 15s, 30s, 60s integration time two times during orbit	1. Compare estimated position of star. / 2. Establish inttime for star measurements / 3. Check PSF	Confirm that star pointing is possible and works with settings	3040	None	Freeze at given time from 90km to 400 km	10	2.2	22
2	1	Limb functional test	Characterize CCD from fullframe images	Test lightly binned images at different altitudes and integration times	point at 50 km, take images with all channels with 1,2 and 4s integration time once during dat and once during night	1. Visually inspect images. / 2. Compare to Sasktran simulations and establish first estimate throughput of system (limb radance → counts) / 3. Compare to Sasktran and establish first estimate pointing error / 4. Use signal at 160 and 200 km at nighttime to estimate dark current, bias. / 5. Use signal at daytime to estimate straylight	Images which are consistent after calibration	3050	None	Point at 50km	36	2.2	79.2
3	1	Limb functional test	Characterize CCD from fullframe images	Test lightly binned images at different altitudes and integration times	point at 50 km, take images with all channels with 8,16 and 32s integration time once during dat and once during night			3051		Point at 50km	36	2.2	79.2
4	1	Limb functional test	Characterize CCD from fullframe images	Test lightly binned images at different altitudes and integration times	point at 70 km, take images with all channels with 1,2 and 4s integration time once during dat and once during night			3050		Point at 70km	36	2.2	79.2
5	1	Limb functional test	Characterize CCD from fullframe images	Test lightly binned images at different altitudes and integration times	point at 70 km, take images with all channels with 8,16 and 32s integration time once during dat and once during night			3051		Point at 70km	36	2.2	79.2
6-15	1	Operational test 1	Test operational mode settings	Run instrument in operational mode 5 (all channels on)	Settings TBD. Photometer 1.5s int time		Fine tune operational mode settings	3101		Point at 92.5km			20	200
16	2	Nadir functional test	Check functionality of Nadir camera	Take full frame images during night using nadir camera	Take full frame images with 1,2 and 4s integration time at night with Nadir camera	Check that signal level is ok (not saturated)	Inttime for nadir	3060		Point at 92.5km	3	2.2	6.6
17	2	Star staring 2	Check accuracy of star staring	Take several picture of star in single channel using same integration time	Start with limb pointing at 90 km and follow star up to 400 km? taking images with IR3 with same integration time (15 s)	1. Compare estimated position of star. / 2. Establish inttime for star measurements / 3. Check PSF	Confirm that star pointing is possible and works with settings	3041	None	Freeze at given time from 90km to 400 km	10	2.2	22
18	2	Limb functional test	Characterize CCD from fullframe images	Test lightly binned images at different altitudes and integration times	point at 90 km, take images with all channels with 1,2 and 4s integration time once during dat and once during night			3050		Point at 90km	36	2.2	79.2
19	2	Limb functional test	Characterize CCD from fullframe images	Test lightly binned images at different altitudes and integration times	point at 90 km, take images with all channels with 8,16 and 32s integration time once during dat and once during night			3051		Point at 90km	36	2.2	79.2
20	2	Limb functional test	Characterize CCD from fullframe images	Test lightly binned images at different altitudes and integration times	point at 110 km, take images with all channels with 1,2 and 4s integration time once during dat and once during night			3050		Point at 110km	36	2.2	79.2
21	2	Limb functional test	Characterize CCD from fullframe images	Test lightly binned images at different altitudes and integration times	point at 110 km, take images with all channels with 8,16 and 32s integration time once during dat and once during night			3051		Point at 110km	36	2.2	79.2
22-30	2	Operational test 2	Test operational mode settings and photometer	Run instrument in operational mode 5 (all channels on)	Settings TBD. Photometer 3s int time		Fine tune operational mode settings	3102		Point at 92.5km			20	180
31	3	Star staring 3	Determine channel alignment	Redo star pointing with single integration time for all channels, two times during orbit	Start with limb pointing at 90 km and follow star up to 400 km? taking images with all channels with specified integration times	Determine channel alignment	Channel alignment	3042	3041	Freeze at given time from 90km to 400 km	12	2.2	26.4
32	3	Nadir functional test 2	Check functionality of Nadir camera	Take binned images with nadir	Take binned images at night with inttime 1,3 and 6 s	Check that signal level is ok (not saturated)	Inttime for nadir in binned mode	3061	3060	Point at 92.5km	3	2.2	<1MB
32	3	Limb functional test	Characterize CCD from fullframe images	Test lightly binned images at different altitudes and integration times	point at 130 km, take images with all channels with 1,2 and 4s integration time once during dat and once during night			3050		Point at 130km	36	2.2	79.2
33	3	Limb functional test	Characterize CCD from fullframe images	Test lightly binned images at different altitudes and integration times	point at 130 km, take images with all channels with 8,16 and 32s integration time once during dat and once during night			3051		Point at 130km	36	2.2	79.2
34	3	Limb functional test	Characterize CCD from fullframe images	Test lightly binned images at different altitudes and integration times	point at 170 km, take images with all channels with 1,2 and 4s integration time once during dat and once during night			3050		Point at 170km	36	2.2	79.2
35	3	Limb functional test	Characterize CCD from fullframe images	Test lightly binned images at different altitudes and integration times	point at 170 km, take images with all channels with 8,16 and 32s integration time once during dat and once during night			3051		Point at 170km	36	2.2	79.2
36-45	3	Operational test 4	Test BG channel binning and photometer	Run instrument in operational mode 5 (all channels on)	Settings TBD. Photometer 6 s int time			3104		Point at 92.5 km			20	200
46	4	Star staring 4	See if read-out streaks disturbs star staring	Redo star pointing with single integration time for all channels but take simultanious snapshot	Start with limb pointing at 90 km and follow star up to 400 km? taking images with all channels with specified integration times	determine if snapshots can be used for star staring	Channel alignment	3043	3042	Freeze at given time from 90km to 400 km	12	2.2	26.4
47	4	Operational test 4	Test planning tool	Run instrument in operational mode 1 (Nadir and UV switching on and off)	TBD			3104	3050/3051	Point at 92.5 km			12
48	4	Limb functional test	Characterize CCD from fullframe images	Test lightly binned images at different altitudes and integration times	point at 230 km, take images with all channels with 1,2 and 4s integration time once during dat and once during night			3050		Point at 230km	36	2.2	79.2
49	4	Limb functional test	Characterize CCD from fullframe images	Test lightly binned images at different altitudes and integration times	point at 230 km, take images with all channels with 8,16 and 32s integration time once during dat and once during night			3051		Point at 230km	36	2.2	79.2
48	4	Dark test 2	Determine stability of dark current in thermal equilibrium	Do binned images (binned calibration) of dark current around orbit with different integrationtime	Look at NP km and take dark images in all limb channels with 1,3,5,10 and 30 s			3061		point at 230 km			20
49	4	Dark test 2	Determine stability of dark current in thermal equilibrium	Do binned images (binned calibration) of dark current around orbit with different integrationtime	Look at NP and take dark images in all limb channels with 1,3,5,10 and 30 s			3061					20
50-60	4	Operational test 5	Test planning tool	Redo operational mode 1 with different integration times (if needed)	TBD			3105	3104	Point at 92.5 km			12	100
61	5	Moon measurement	Do measurement of moon	Moon measurement from all channels	Start with limb pointing at 90 km and follow star up to 400 km? taking images with all channels with specified integration time		Relative calibration	3070	3043	Freeze at given time from 90km to 400 km	12	2.2	26.4
62	5	Moon measurement	Do measurement of moon	Moon measurement from all channels	Start with limb pointing at 90 km and follow star up to 400 km? taking images with all channels with specified integration time		Relative calibration	3070	3043	Freeze at given time from 90km to 400 km	12	2.2	26.4
63	5	Moon measurement	Do measurement of moon	Moon measurement from all channels	Start with limb pointing at 90 km and follow star up to 400 km? taking images with all channels with specified integration time		Relative calibration	3070	3043	Freeze at given time from 90km to 400 km	12	2.2	26.4
64	5	Moon measurement	Do measurement of moon	Moon measurement from all channels	Start with limb pointing at 90 km and follow star up to 400 km? taking images with all channels with specified integration time		Relative calibration	3070	3043	Freeze at given time from 90km to 400 km	12	2.2	26.4
65	5	Moon measurement	Do measurement of moon	Moon measurement from all channels	Start with limb pointing at 90 km and follow star up to 400 km? taking images with all channels with specified integration time		Relative calibration	3070	3043	Freeze at given time from 90km to 400 km	12	2.2	26.4
66	5	Moon measurement	Do measurement of moon	Moon measurement from all channels	Start with limb pointing at 90 km and follow star up to 400 km? taking images with all channels with specified integration time		Relative calibration	3070	3043	Freeze at given time from 90km to 400 km	12	2.2	26.4
67-90	5	Operational test 5	Test planning tool	Redo operational mode 1 with possible bug fixes	TBD			3105		Point at 92.5 km			10	200
	6	Analysis day
91	7	Star staring 5	Redo normal star staring to look at consistency of measurements	Redo star pointing with single integration time for all channels	Start with limb pointing at 90 km and follow star up to 400 km? taking images with all channels with specified integration time	determine star staring consistency	Channel alignment	3042	3043	Freeze at given time from 90km to 400 km	12	2.2	26.4
92	7	Dark test 1	Determine stability of dark current in thermal equilibrium	Do 2 fullframe images looking at NP km with all limb channels, do 2*1s 2*2 s etc	Look at NP and take dark images in all limb channels with 1,3, 5, 10, 15 and 30 s			3060		point at 230 km	60	2.2	132
93	7	Rayleigh step	Get statistics on rayleigh atmosphere for calibration	Do images binned calibration looking at 60 km				3080		Look at 60 km			20
94	7	Rayleigh step		Do images binned calibration looking at 90 km				3080		Look at 90 km			20
95	7	Rayleigh step		Do images binned calibration looking at 120 km				3080		Look at 120 km			20
96	7	Rayleigh sweep		Do binned calibration				3090		Sweep between 50-150 km			20
96-105	7	Operational test 5	Test planning tool	Redo operational mode 1 with possible bug fixes	TBD			3105		Point at 92.5 km			10	100
106	8	Star staring 6	Contigency or look at moon										0
107	8	Nadir limb test	Establish Nadir camera performance	Fullframe images	Look at limb with nadir at altitude 50 and 70 km fullframe inttime 1,5 and 10, 20 and 30 s			3110		Point at limb with Nadir!	20	2.2	44
108	8	Nadir limb test	Establish Nadir camera performance	Fullframe images	Look at limb with nadir at altitude 90 and 110 km fullframe inttime 1,5 and 10, 20 and 30 s			3110			20	2.2	44
109	8	Nadir limb test	Establish Nadir camera performance	Fullframe images	Look at limb with nadir at altitude 110 and 130 km fullframe inttime 1,5 and 10, 20 and 30 s			3110			20	2.2	44
110	8	Nadir limb test	Establish Nadir camera performance	Fullframe images	Look at limb with nadir at altitude 170 km and 230 km fullframe inttime 1,5 and 10, 20 and 30 s			3110			20	2.2	44
111	8	Nadir limb test 2	Establish Nadir camera performance	Binned images	Look at limb with nadir at altitude 170 km and 230 km binned inttime 1,5 and 10, 20 and 30 s			3110					10
112-120	8	Turn off instrument	Cool down instrument
	9	Cool down instrument day
121	10	Thermal resolution test	Star staring					3024		Freeze at given time from 90km to 400 km			80
122	10	Thermal dark current test	Dark current binned					3061		NP looking			20
123	10	Thermal resolution test	Star staring					3024		Freeze at given time from 90km to 400 km			80
124	10	Thermal dark current test	Dark current binned					3061		NP looking			20
125	10	Thermal resolution test	Star staring					3024		Freeze at given time from 90km to 400 km			80
126	10	Thermal dark current test	Dark current binned					3061		NP looking			20
127-135	10	Operational test 5	Test planning tool	Redo operational mode 1 with possible bug fixes	TBD			3106		Point at 92.5 km			10	100
136	11	JPEG Test						3120					20
137	11	JPEG Test						3120					20
138	11	Polarisation test						3130		Perform roll manouver +- 45 degree along the orbit			50
139	11	Polarisation test						3130					50
140	11	WDW test						3140					20
141	11	WDW test						3140					20
142-150	11	Operational mode 1						1100
150-165	12	Limb ground target test						3150		Look at ground target with limb image day and night			50
165-180	13	Odin co-incident measurments						3160		Look out of orbit (<5 degrees) to get coincident measurements with Odin			20
180-195	14	Contigency
195-210	15	Contigency
210--	16	Transition into operations