## Sheet1
Pass # / orbit	Day	test name	Goal	Description	Detailed Decription	Outcome	Procedure ID	Dependency	Platform actions	number of images	size/image	Expected data in next pass)	Cumulated data (over night)
0	D-1		Heat instrument	Turn on instrument	Turn on payload, heaters and CCDs	Equilibrium temperatures	-	-	-	0	-	<1MB
1	1	Star staring 1	Prove star finding capacity	Take pictures of stars with single channel	Start with limb pointing at 90 km and follow star for 4 minutes. Take images with IR3 with 5s, 15s, 30s, 60s, 90s integration time two times during orbit	Confirm that star pointing is possible and determine optimal settings	3040		Freeze at given time from 90km to -5 degree pitch	10	2.2	22
2	1	Limb functional test	Characterize CCD from fullframe images	Test fullframe images at different altitudes and integration times	Point at 50 km, take images with all channels with 1,2, 4s and 8s integration time once during day and once during night	Images which are consistent after calibration	3050		Point at 50km	48	2.2	105.6
3	1	Limb functional test	Characterize CCD from fullframe images	Test fullframe images at different altitudes and integration times	Point at 50 km, take images with all channels with 16 and 32s integration time once during day and once during night		3051		Point at 50km	24	2.2	52.8
4	1	Star tracking	Check start tracking consistency between Freeze and OHB	OHB track stars	take fullframe images with IR3 5, 15, 30 and 60s.		3200		OHB tracking	10	2.2	22
5	1	Limb functional test	Characterize CCD from fullframe images	Test fullframe images at different altitudes and integration times	Point at 70 km, take images with all channels with 1,2 4s and 8s integration time once during day and once during night		3050		Point at 70km	48	2.2	105.6
6	1	Limb functional test	Characterize CCD from fullframe images	Test fullframe images at different altitudes and integration times	Point at 70 km, take images with all channels with 16 and 32s integration time once during day and once during night		3051		Point at 70km	24	2.2	52.8
6-15	1	Operational test 1	Test operational mode settings	Run instrument in operational mode 5 (custom binning)	Settings TBD. Photometer 1.5s int time	Fine tune operational mode settings for channels IR1, IR2, UV1, UV2	3101		Point at 92.5km			20	200
16	2	Nadir functional test	Check functionality of Nadir camera	Take full frame images during night using nadir camera	Take full frame images with 1,2 and 4s integration time at night with Nadir camera	Inttime for nadir	3060		Point at 92.5km	3	2.2	6.6
17	2	Star staring 2	Check accuracy of star staring	Take several picture of star in single channel using same integration time	Start with limb pointing at 90 km and follow star for 4 minutes. Take images with IR3 with 30s integration time (TBD).	Estimate accuracy of star staring	3042	3040	Freeze at given time from 90km to -5 degree pitch	6	2.2	13.2
18	2	Limb functional test	Characterize CCD from fullframe images	Test fullframe images at different altitudes and integration times	Point at 90 km, take images with all channels with 1,2, 4s and 8s integration time once during day and once during night		3050		Point at 90km	48	2.2	105.6
19	2	Limb functional test	Characterize CCD from fullframe images	Test fullframe images at different altitudes and integration times	Point at 90 km, take images with all channels with 16 and 32s integration time once during day and once during night		3051		Point at 90km	24	2.2	52.8
20	2	Limb functional test	Characterize CCD from fullframe images	Test fullframe images at different altitudes and integration times	Point at 110 km, take images with all channels with 1,2,4 and 8s integration time once during day and once during night		3050		Point at 110km	48	2.2	105.6
21	2	Limb functional test	Characterize CCD from fullframe images	Test fullframe images at different altitudes and integration times	point at 110 km, take images with all channels with 16 and 32s integration time once during day and once during night		3051		Point at 110km	24	2.2	52.8
22-30	2	Operational test 2	Test operational mode settings and photometer	Run instrument in operational mode 5 (operational binning)	Settings TBD. Photometer 3s int time. Nadir image binning iteration	Check linearity of photometer, Check settings for nadir camera, Check settings for BG channels	3102		Point at 92.5km	3101		20	180
31	3	Star staring 3	Determine channel alignment	Redo star pointing with single integration time for all channels, two times during orbit	Start with limb pointing at 90 km and follow star for 4 minutes. Take full frame images with all channels with TBD inttime	Channel alignment	3043	3042	Freeze at given time from 90km to -5 degree pitch	12	2.2	26.4
32	3	Nadir functional test 2	Check functionality of Nadir camera	Take binned images with nadir	Take binned images at night with inttime 1,3 and 6s and binning of factor 2 and 4 less than normal	Inttime for nadir in binned mode	3061	3060	Point at 92.5km	9		<1MB
32	3	Limb functional test	Characterize CCD from fullframe images	Test fullframe images at different altitudes and integration times	point at 130 km, take images with all channels with 1,2, 4 and 8s integration time once during day and once during night		3050		Point at 130km	48	2.2	105.6
33	3	Limb functional test	Characterize CCD from fullframe images	Test fullframe images at different altitudes and integration times	point at 130 km, take images with all channels with 16 and 32s integration time once during day and once during night		3051		Point at 130km	24	2.2	52.8
34	3	Limb functional test	Characterize CCD from fullframe images	Test fullframe images at different altitudes and integration times	point at 170 km, take images with all channels with 1,2, 4, 8s integration time once during day and once during night		3050		Point at 170km	48	2.2	105.6
35	3	Limb functional test	Characterize CCD from fullframe images	Test fullframe images at different altitudes and integration times	point at 170 km, take images with all channels with 16 and 32s integration time once during day and once during night		3051		Point at 170km	24	2.2	52.8
36-45	3	Operational test 3	Test BG channel binning and photometer	Run instrument in operational mode 5 (operational binning)	Settings TBD. Photometer 6 s int time	Check linearity of photometer, determine settings for operational mode	3103	3102	Point at 92.5 km	3102		20	200
46	4	Star staring 4	See if read-out streaks disturbs star staring	Redo star pointing with single integration time for all channels but take simultanious snapshot	Start with limb pointing at 90 km and follow star for 4 minutes. Take full frame images with all channels with TBD inttime	Channel alignment and possible streak characterization	3044	3043	Freeze at given time from 90km to -5 degree pitch	12	2.2	26.4
47	4	Operational test 4	Test planning tool	Run instrument in operational mode 1 (Nadir and UV switching on and off)	TBD		3104	3102	Point at 92.5 km			12
48	4	Limb functional test	Characterize CCD from fullframe images	Test fullframe images at different altitudes and integration times	point at 230 km, take images with all channels with 1,2,4, 8s integration time once during day and once during night		3050		Point at 230km	48	2.2	105.6
49	4	Limb functional test	Characterize CCD from fullframe images	Test fullframe images at different altitudes and integration times	point at 230 km, take images with all channels with 16 and 32s integration time once during day and once during night		3051		Point at 230km	24	2.2	52.8
48	4	Dark test 1	Determine stability of dark current in thermal equilibrium	Do 2 fullframe images looking at NP km with all limb channels, do 2*1s 2*2 s etc	Look at NP and take dark images in all limb channels with 1,3, 5, 10, 15 and 30 s		3060		point at 230 km	60	2.2	132
49	4	Dark test 2	Determine stability of dark current in thermal equilibrium	Do binned images (binned calibration) of dark current around orbit with different integrationtime	Look at NP and take dark images in all limb channels with 1,3,5,10 and 30 s		3061					20
50-60	4	Operational test 5	Test planning tool	Switch to mode 1 (without yaw)	TBD		3105	3104	Point at 92.5 km			12	100
61	5	Moon measurement	Do measurement of moon	Moon measurement from all channels	Start with limb pointing at 90 km and follow star for 4 minutes. Take full frame images with all channels with TBD inttime	Relative calibration	3070	3044	Freeze at given time from 90km to -5 degree pitch	12	2.2	26.4
62	5	Moon measurement	Do measurement of moon	Moon measurement from all channels	Start with limb pointing at 90 km and follow star for 4 minutes. Take full frame images with all channels with TBD inttime	Relative calibration	3070	3044	Freeze at given time from 90km to -5 degree pitch	12	2.2	26.4
63	5	Moon measurement	Do measurement of moon	Moon measurement from all channels	Start with limb pointing at 90 km and follow star for 4 minutes. Take full frame images with all channels with TBD inttime	Relative calibration	3070	3044	Freeze at given time from 90km to -5 degree pitch	12	2.2	26.4
64	5	Moon measurement OHB	Do measurement of moon using OHB tracking	Moon measurement from all channels	Start with limb pointing at 90 km and follow star for 4 minutes. Take full frame images with all channels with TBD inttime	Relative calibration	3210	3044	OHB tracking	12	2.2	26.4
65	5	Moon measurement	Do measurement of moon	Moon measurement from all channels	Start with limb pointing at 90 km and follow star for 4 minutes. Take full frame images with all channels with TBD inttime	Relative calibration	3070	3044	Freeze at given time from 90km to -5 degree pitch	12	2.2	26.4
66-90	5	Operational test 5	Test planning tool	Redo operational mode 1 with possible bug fixes	TBD		3105		Point at 92.5 km			10	200
	6	Analysis day/Coll down instrument
121	7	Thermal resolution test	Star staring				3024		Freeze at given time from 90km to 400 km			80
122	7	Thermal dark current test	Dark current binned				3061		NP looking			20
123	7	Thermal resolution test	Star staring				3024		Freeze at given time from 90km to 400 km			80
124	7	Thermal dark current test	Dark current binned				3061		NP looking			20
125	7	Thermal resolution test	Star staring				3024		Freeze at given time from 90km to 400 km			80
126	7	Thermal dark current test	Dark current binned				3061		NP looking			20
127-135	7	Operational test 6	Test planning tool	Add yaw to operational mode	TBD		3106		Point at 92.5 km			10	100
91	8	Star staring 5	Redo normal star staring to look at consistency of measurements	Redo star pointing with single integration time for all channels	Start with limb pointing at 90 km and follow star for 4 minutes. Take full frame images with all channels with TBD inttime	Channel alignment	3042	3043	Freeze at given time from 90km to -5 degree pitch	12	2.2	26.4
92	8	Dark test 3	Determine stability of dark current in thermal equilibrium yawing out of orbit plane	Do 2 fullframe images looking at NP km with all limb channels, do 2*1s 2*2 s etc	Pitch down 5 degrees and yaw away from sun and take dark images in all limb channels with 1,3, 5, 10, 15 and 30 s		3062		Pitch down 5 degrees and yaw away from sun	60	2.2	132
93	8	Rayleigh step	Get statistics on rayleigh atmosphere for calibration	Do images binned calibration looking at 60 km			3080		Look at 60 km			20
94	8	Rayleigh step		Do images binned calibration looking at 90 km			3080		Look at 90 km			20
95	8	Rayleigh step		Do images binned calibration looking at 120 km			3080		Look at 120 km			20
96	8	Rayleigh sweep		Do binned calibration			3090		Sweep between 50-150 km			20
96-105	8	Operational test 6	Test planning tool	Redo operational mode 1 with possible bug fixes	TBD		3106		Point at 92.5 km			10	100
106	9	Star staring 6	Contigency or look at moon									0
107	9	Nadir limb test	Establish Nadir camera performance	Fullframe images	Look at limb with nadir at altitude 60 km and 90 km fullframe inttime 1,5 and 10, 20 and 30 s		3110		Point at limb with Nadir!	20	2.2	44
108	9	Nadir limb test	Establish Nadir camera performance	Fullframe images	Look at limb with nadir at altitude 120 and 150 km fullframe inttime 1,5 and 10, 20 and 30 s		3110			20	2.2	44
109	9	Nadir limb test	Establish Nadir camera performance	Fullframe images	Look at limb with nadir at altitude 190 and 230 km fullframe inttime 1,5 and 10, 20 and 30 s		3110			20	2.2	44
110	9	Nadir limb test	Establish Nadir camera performance	Fullframe images	Look at limb with nadir at altitude 170 km and 230 km fullframe inttime 1,5 and 10, 20 and 30 s		3110			20	2.2	44
111	9	Nadir limb test 2	Establish Nadir camera performance	Binned images	Look at limb with nadir at altitude 170 km and 230 km binned inttime 1,5 and 10, 20 and 30 s		3110					10
112-120	9	Turn off instrument	Cool down instrument
136	10	JPEG Test					3120					20
137	10	JPEG Test					3120					20
138	10	Polarisation test					3130		Perform roll manouver +- 45 degree along the orbit			50
139	10	Polarisation test					3130					50
140	10	WDW test					3140					20
141	10	WDW test					3140					20
142-150	10	Operational mode 1					1100
150-165	11	Limb ground target test					3150		Look at ground target with limb image day and night			50
165-180	12	Odin co-incident measurments					3160		Look out of orbit (<5 degrees) to get coincident measurements with Odin			20
180-195	13	Contigency
195-210	14	Contigency
210--	15	Transition into operations