## timeline_schedule
start_date	end_date	id	name	version	standard_altitude	yaw_correction	pointing_altitudes	xml_file	description_short	description_long
2022-11-22 08:15:00	2022-11-22 09:25:00	3040	STAR	1	92500	False	[92500]	STP-MTS-3040_22112222112001STAR.xml	Star freeze	Start with limb pointing at 90 km and follow star for 4 minutes. Take images with IR3 with 5s, 15s, 30s, 60s, 90s integration times
2022-11-22 09:30:00	2022-11-22 12:45:00	3050	LMBF	1	92500	False	[230000, 230000]	STP-MTS-3050_22112222112001LMBF.xml	Limb functional	Point at 230 km, take fullframe images with all channels with 1,2, 4s and 8s integration time once during day and once during night / Point at 230 km, take fullframe images with all channels with 16 and 32s integration time once during day and once during night
2022-11-22 12:45:00	2022-11-22 14:20:00	2020	SNAPT4	1	92500	False		SKS-MTS-2020-22112222112001SNAPT4.xml	Star ECI pointing	Start with limb pointing at 90 km and follow star for 4 minutes using OHB ECI staring manouver. Take images with IR3 with 5s, 15s, 30s, 60s integration times
2022-11-22 14:20:00	2022-11-22 17:35:00	3051	LMBF	1	92500	False	[70000, 70000]	STP-MTS-3051_22112222112001LMBF.xml	Limb functional	Point at 70 km, take fullframe images with all channels with 1,2 4s and 8s integration time once during day and once during night / Point at 70 km, take fullframe images with all channels with 16 and 32s integration time once during day and once during night
2022-11-22 17:45:00	2022-11-23 07:43:20	3101	MODE5	1	92500	False	[]	STP-MTS-3101_22112222112001MODE5.xml	Operational mode	Binned calibration, WDW128, TEXPUV = 5000, TEXPIR = 5000, TEXPBG = 5000, TEXPHO = 1500
2022-11-23 08:10:00	2022-11-23 09:40:00	3060	NADF	1	92500	False	[92500]	STP-MTS-3060_22112322112101NADF.xml	Nadir functional	Take full frame images with 1,2 and 4s integration time at night with Nadir camera
2022-11-23 10:00:00	2022-11-23 14:45:00	3052	LMBF	2	92500	False	[90000, 90000, 110000]	STP-MTS-3052_22112322112202LMBF.xml	Limb functional	Point at 90 km, take fullframe images with all channels with 1,2, 4s and 8s integration time once during day and once during night / Point at 90 km, take fullframe images with all channels with 16 and 32s integration time once during day and once during night / Point at 110 km, take fullframe images with all channels with 1,2,4 and 8s integration time once during day and once during night
2022-11-23 14:50:00	2022-11-23 16:50:00	3040	STAR	3	92500	False	[92500]	STP-MTS-3040_22112322112303STAR.xml	Star freeze	Start with limb pointing at 90 km and follow star for 4 minutes. Take images with IR3 with 5s, 15s, 30s, 60s, 90s integration times
2022-11-23 16:10:00	2022-11-23 18:10:00	3053	LMBF	3	92500	False	[110000]	STP-MTS-3053_22112322112303LMBF.xml	Limb functional	Point at 110 km, take fullframe images with all channels with 16 and 32s integration time once during day and once during night
2022-11-23 18:00:00	2022-11-24 06:00:00	3102	MODE5	2	92500	False	[]	STP-MTS-3102_22112322112302MODE5.xml	Operational mode	Operational binning, WDW128, TEXPUV = 5000, TEXPIR = 5000, TEXPBG = 5000, TEXPHO = 3000
2022-11-24 09:30:00	2022-11-24 10:00:00	3060	NADF	2	92500	False	[92500]	STP-MTS-3060_22112422112302NADF.xml	Nadir functional	Take full frame images during night using nadir camera
2022-11-24 10:00:00	2022-11-24 13:30:00	3054	LMBF	2	92500	False	[130000, 130000]	STP-MTS-3054_22112422112302LMBF.xml	Limb functional	Point at 130 km, take images with all channels with 1,2, 4s and 8s integration time once during day and once during night / Point at 130 km, take images with all channels with 16 and 32s integration time once during day and once during night
2022-11-24 13:30:00	2022-11-24 17:00:00	3055	LMBF	2	92500	False	[50000, 50000]	STP-MTS-3055_22112422112302LMBF.xml	Limb functional	Point at 50 km, take images with all channels with 1,2, 4s and 8s integration time once during day and once during night / Point at 50 km, take images with all channels with 16 and 32s integration time once during day and once during night
2022-11-25 18:00:00	2022-11-28 18:00:00	3170	PHOTO	1	92500	False	[]	STP-MTS-3170_22112522112501PHOTO.xml	Photometer only	Run only photometer TEXPHO=6000
2022-11-28 10:00:00	2022-11-28 11:00:00	3180	SIMRAC	1	92500	False	[230000]	STP-MTS-3180_22112822112501SIMRAC.xml	Simultaneous readout	Take simulatanious readout 2 and 2 channels of dark sky with 5 and 15 s integration time
2022-11-28 11:30:00	2022-11-28 13:00:00	3181	SIMR2C	1	92500	False	[230000]	STP-MTS-3181_22112822112501SIMR2C.xml	Simultaneous readout	Take simulatanious readout all channels with 5 and 15 s integration time
2022-11-28 14:00:00	2022-11-28 16:59:58	3080	RAY60	1	60000	False	[]	STP-MTS-3080_22112222112501RAY60.xml	Rayleigh stare	Do images binned calibration looking at 60 km. Take WDW 7 images with binned calibration but 12 sec exposure intervall.
2022-11-28 17:00:00	2022-11-28 19:59:58	3080	RAY90	1	90000	False	[]	STP-MTS-3080_22112222112501RAY90.xml	Rayleigh stare	Do images binned calibration looking at 90 km. Take WDW 7 images with binned calibration but 12 sec exposure intervall.
2022-11-28 20:00:00	2022-11-28 22:59:58	3080	RAY120	1	120000	False	[]	STP-MTS-3080_22112222112501RAY120.xml	Rayleigh stare	Do images binned calibration looking at 120 km. Take WDW 7 images with binned calibration but 12 sec exposure intervall.
2022-11-29 08:30:00	2022-11-29 10:30:00	3040	STAR	4	92500	False	[92500]	STP-MTS-3040_22112922112804STAR.xml	Star freeze	Take image with all channels staggered with 15s integration time
2022-11-29 10:30:00	2022-11-29 12:30:00	3040	STAR	5	92500	False	[92500]	STP-MTS-3040_22112922112805STAR.xml	Star freeze	Take image with all channels staggered with 15s integration time
2022-11-29 12:00:00	2022-11-29 14:00:00	3042	STAR	1	92500	False	[92500]	STP-MTS-3042_22112922112801STAR.xml	Star freeze (Simultaneous readout)	Take image with all channels simultaniously with 15s integration time
2022-11-29 13:00:00	2022-11-29 15:00:00	3040	STAR	6	92500	False	[92500]	STP-MTS-3040_22112922112806STAR.xml	Star freeze	Take image with all channels staggered with 15s integration time
2022-11-29 18:00:00	2022-11-29 23:59:58	3103	MODE1	3	92500	False	[]	STP-MTS-3103_22112922112803MODE1.xml	Operational mode	Mode 1. Operational binning, WDW128, TEXPUV = 5000, TEXPIR = 5000, TEXPBG = 1500, TEXPHO = 3000
2022-11-30 02:00:00	2022-11-30 04:00:00	3070	MOON	1	90000	False	[92500]	STP-MTS-3070_22113022112901MOON.xml	Moon freeze	Take image of moon using freeze with all channels 2 and 15s integration time
2022-11-30 04:00:00	2022-11-30 06:00:00	3070	MOON	2	90000	False	[90000]	STP-MTS-3070_22113022112902MOON.xml	Moon freeze	Take image of moon using freeze with all channels 2 and 15s integration time
2022-11-30 06:00:00	2022-11-30 07:00:00	3070	MOON	3	90000	False	[90000]	STP-MTS-3070_22113022112903MOON.xml	Moon freeze	Take image of moon using freeze with all channels 2 and 15s integration time
2022-11-30 07:30:00	2022-11-30 08:30:00	3070	MOON	4	90000	False	[90000]	STP-MTS-3070_22113022112904MOON.xml	Moon freeze	Take image of moon using freeze with all channels 2 and 15s integration time
2022-11-30 09:00:00	2022-11-30 10:00:00	3070	MOON	5	90000	False	[90000]	STP-MTS-3070_22113022112905MOON.xml	Moon freeze	Take image of moon using freeze with all channels 2 and 15s integration time
2022-11-30 11:00:00	2022-11-30 12:00:00	3070	MOON	6	90000	False	[90000]	STP-MTS-3070_22113022112906MOON.xml	Moon freeze	Take image of moon using freeze with all channels 2 and 15s integration time
2022-11-30 12:30:00	2022-11-30 13:30:00	3070	MOON	7	90000	False	[90000]	STP-MTS-3070_22113022112907MOON.xml	Moon freeze	Take image of moon using freeze with all channels 2 and 15s integration time
2022-11-30 13:30:00	2022-11-30 17:30:00	3062	DARK3	1	92500	False	[90000, 90000]	STP-MTS-3062_22113022112901DARK3.xml	Dark image with yaw	Take full frame dark images yawing away from the sun. 10s integration time all channels (incl nadir)
2022-11-30 18:00:00	2022-12-01 05:59:58	3103	MODE1	3	92500	True	[]	STP-MTS-3103_22113022112803MODE1.xml	Operational mode 1	Mode 1. Operational binning, WDW128, TEXPUV = 5000, TEXPIR = 5000, TEXPBG = 1500, TEXPHO = 3000
2022-12-01 11:00:00	2022-12-01 14:29:58	3130	POL	1	92500	False	[]	STP-MTS-3130_22120122113001POL.xml	Polarisation measurements
2022-12-01 18:00:00	2022-12-01 23:59:58	3103	MODE1	4	92500	False	[]	STP-MTS-3103_22120122113004MODE1.xml	Operational mode	Mode 1. Operational binning, WDW128, TEXPUV = 5000, TEXPIR = 5000, TEXPBG = 1500, TEXPHO = 3000
2022-12-02 04:00:00	2022-12-02 05:00:00	3120	CROP	1	92500	False	[]	STP-MTS-3120_22120222113001CROP.xml	Crop test	Full frame readout with full and half of image cropped in all channels
2022-12-02 11:00:00	2022-12-02 13:00:00	3110	NADLMB	1	92500	False	[]	STP-MTS-3110_22120222113001NADLMB.xml	Limb in Nadir
2022-12-02 20:00:00	2022-12-02 21:29:58	3160	ODIN1	1	90000	False	[]	STP-MTS-3160_22120222120101ODIN1.xml	Odin co-aligned
2022-12-02 23:00:00	2022-12-03 00:29:58	3161	ODIN2	1	90000	False	[]	STP-MTS-3161_22120222120101ODIN2.xml	Odin co-aligned
2022-12-03 12:00:00	2022-12-03 23:59:58	3104	MODE5	1	92500	False	[]	STP-MTS-3104_22120322120201MODE5.xml	Operational mode
2022-12-04 12:00:00	2022-12-04 23:59:58	3104	MODE1y	1	92500	True	[]	STP-MTS-3104_22120422120201MODE1y.xml	Operational mode 1
2022-12-05 06:00:00	2022-12-05 17:59:58	3105	MODE1y	1	92500	True	[]	STP-MTS-3105_22120522120201MODE1y.xml	Operational mode 1 with JPEG