## Sheet1
start_date	end_date	id	name	version	standard_altitude	yaw_correction	pointing_altitudes	Description	Detailed Decription
2022-11-22 08:15:00	2022-11-22 09:25:00	3040	STAR	1	92500	False	[92500]	Start with limb pointing at 90 km and follow star for 4 minutes. Take images with IR3 with 5s, 15s, 30s, 60s, 90s integration times
2022-11-22 09:30:00	2022-11-22 12:45:00	3050	LMBF	1	92500	False	[230000, 230000]	Point at 230 km, take images with all channels with 1,2, 4s and 8s integration time once during day and once during night / Point at 230 km, take images with all channels with 16 and 32s integration time once during day and once during night
2022-11-22 14:20:00	2022-11-22 17:35:00	3051	LMBF	1	92500	False	[70000, 70000]	Point at 70 km, take images with all channels with 1,2 4s and 8s integration time once during day and once during night / Point at 70 km, take images with all channels with 16 and 32s integration time once during day and once during night
OHB star tracking								take fullframe images with IR3 5, 15, 30 and 60s.
2022-11-22 17:45:00	2022-11-23 07:45:00	3101	MODE5	1	92500	False	[]	Binned calibration WDW128, TEXPUV = 5000, TEXPIR = 5000, TEXPBG = 5000, TEXPHO = 1500
2022-11-23 08:10:00	2022-11-23 09:40:00	3060	NADF	1	92500	False	[92500]	Take full frame images with 1,2 and 4s integration time at night with Nadir camera
2022-11-23 09:45:00	2022-11-23 11:00:00	3041	STAR	1	92500	False	[92500]	Start with limb pointing at 90 km and follow star for 4 minutes. Take images with IR3 with 5s, 15s, 30s, 60s, 90s integration times
2022-11-23 10:00:00	2022-11-23 14:45:00	3052	LMBF	2	92500	False	[90000, 90000, 110000]	Point at 90 km, take images with all channels with 1,2, 4s and 8s integration time once during day and once during night / Point at 90 km, take images with all channels with 16 and 32s integration time once during day and once during night / Point at 110 km, take images with all channels with 1,2,4 and 8s integration time once during day and once during night
2022-11-23 11:20:00	2022-11-23 14:35:00	3052	LMBF	1	92500	False	[90000, 90000]	Take full frame images during night using nadir camera
2022-11-23 14:30:00	2022-11-23 17:45:00	3053	LMBF	1	92500	False	[90000, 90000, 110000, 110000]	Test fullframe images at different altitudes and integration times	Point at 90 km, take images with all channels with 1,2, 4s and 8s integration time once during day and once during night
2022-11-23 14:50:00	2022-11-23 16:50:00	3040	STAR	3	92500	False	[92500]	Test fullframe images at different altitudes and integration times	Point at 90 km, take images with all channels with 16 and 32s integration time once during day and once during night
2022-11-23 16:10:00	2022-11-23 18:10:00	3053	LMBF	3	92500	False	[110000]	Test fullframe images at different altitudes and integration times	Point at 110 km, take images with all channels with 1,2,4 and 8s integration time once during day and once during night
2022-11-23 17:45:00	2022-11-24 07:45:00	3102	MODE5	1	92500	False	[]	Take pictures of stars with single channel	Start with limb pointing at 90 km and follow star for 4 minutes. Take images with IR3 with 5s, 15s, 30s, 60s, 90s integration times
2022-11-23 18:00:00	2022-11-24 06:00:00	3102	MODE5	2	92500	False	[]	Test fullframe images at different altitudes and integration times	point at 110 km, take images with all channels with 16 and 32s integration time once during day and once during night
2022-11-24 09:30:00	2022-11-24 10:00:00	3060	NADF	2	92500	False	[92500]	Run instrument in operational mode 5 (operational binning)	Settings TBD. Photometer 3s int time. background image binning iteration
2022-11-24 10:00:00	2022-11-24 13:30:00	3054	LMBF	2	92500	False	[130000, 130000]	Take several picture of star in single channel using same integration time	Start with limb pointing at 90 km and follow star for 4 minutes. Take images with IR3 with 30s integration time (TBD).
2022-11-24 13:30:00	2022-11-24 17:00:00	3055	LMBF	2	92500	False	[50000, 50000]	Redo star pointing with single integration time for all channels, two times during orbit	Start with limb pointing at 90 km and follow star for 4 minutes. Take full frame images with all channels with TBD inttime
2022-11-25 08:00:00	2022-11-25 17:00:00	3040	STAR	4	92500	False	[92500, 92500, 92500, 92500, 92500]	Take binned images with nadir	Take binned images at night with inttime 1,3 and 6s and binning of factor 2 and 4 less than normal
2022-11-25 18:00:00	2022-11-28 18:00:00	3170	PHOTO	1	92500	False	[]	Take full frame images during night using nadir camera	Take full frame images with 1,2 and 4s integration time at night with Nadir camera
2022-11-28 10:00:00	2022-11-28 11:00:00	3180	SIMRAC	1	92500	False	[230000]	Test fullframe images at different altitudes and integration times	point at 130 km, take images with all channels with 1,2, 4 and 8s integration time once during day and once during night
2022-11-28 11:30:00	2022-11-28 13:00:00	3181	SIMR2C	1	92500	False	[230000]	Test fullframe images at different altitudes and integration times	point at 130 km, take images with all channels with 16 and 32s integration time once during day and once during night
2022-11-28 14:00:00	2022-11-28 17:00:00	3080	RAY60	1	60000	False	[]	Test fullframe images at different altitudes and integration times	point at 50 km, take images with all channels with 1,2, 4, 8s integration time once during day and once during night
2022-11-28 17:00:00	2022-11-28 20:00:00	3080	RAY90	1	90000	False	[]	Test fullframe images at different altitudes and integration times	Point at 50 km, take images with all channels with 16 and 32s integration time once during day and once during night
2022-11-28 20:00:00	2022-11-28 23:00:00	3080	RAY120	1	120000	False	[]	Run instrument in operational mode 5 (operational binning)	Settings TBD. Photometer 3 s int time
2022-11-29 08:30:00	2022-11-29 10:30:00	3040	STAR	4	92500	False	[92500]	Use OHB ECI pointing and point at star and star +- 3 degrees horisontal and +-0.7 degrees vertical	take images all channels 15s intetime
2022-11-29 10:30:00	2022-11-29 12:30:00	3040	STAR	5	92500	False	[92500]	Run instrument with photometers only	Photometer 6 s int time
2022-11-29 12:00:00	2022-11-29 14:00:00	3042	STAR	1	92500	False	[92500]	Redo star pointing with single integration time for all channels but take simultanious snapshot	Start with limb pointing at 90 km and follow star for 4 minutes. Take full frame images with all channels with TBD inttime
2022-11-29 13:00:00	2022-11-29 15:00:00	3040	STAR	6	92500	False	[92500]	Run instrument in operational mode 1 (Nadir and UV switching on and off)	TBD
2022-11-29 18:00:00	2022-11-30 00:00:00	3103	MODE1	3	92500	False	[]	Test fullframe images at different altitudes and integration times	point at 170 km, take images with all channels with 1,2,4, 8s integration time once during day and once during night
2022-11-30 02:00:00	2022-11-30 04:00:00	3040	STAR	5	92500	False	[92500]	Test fullframe images at different altitudes and integration times	Point at 170 km, take images with all channels with 16 and 32s integration time once during day and once during night
2022-11-30 02:00:00	2022-11-30 04:00:00	3070	MOON	1	90000	False	[92500]	Do 2 fullframe images looking at NP km with all limb channels, do 2*1s 2*2 s etc	Look at NP and take dark images in all limb channels with 1,3, 5, 10, 15 and 30 s
2022-11-30 04:00:00	2022-11-30 06:00:00	3070	MOON	2	90000	False	[90000]	Do binned images (binned calibration) of dark current around orbit with different integrationtime	Look at NP and take dark images in all limb channels with 1,3,5,10 and 30 s
2022-11-30 06:00:00	2022-11-30 07:00:00	3070	MOON	3	90000	False	[90000]	Switch to mode 1 (without yaw)	TBD
2022-11-30 07:30:00	2022-11-30 08:30:00	3070	MOON	4	90000	False	[90000]	Take simulatanious readout all channels with 5 and 15 s integration time
2022-11-30 09:00:00	2022-11-30 10:00:00	3070	MOON	5	90000	False	[90000]	Take simulatanious readout 2 and 2 channels of dark sky with 5 and 15 s integration time
2022-11-30 11:00:00	2022-11-30 12:00:00	3070	MOON	6	90000	False	[90000]	Do images binned calibration looking at 60 km	Take WDW 7 images with binned calibration bu 12 sec exposure intervall
2022-11-30 12:30:00	2022-11-30 13:30:00	3070	MOON	7	90000	False	[90000]	Do images binned calibration looking at 90 km	Take WDW 7 images with binned calibration bu 12 sec exposure intervall
2022-11-30 13:30:00	2022-11-30 17:30:00	3062	DARK3	1	92500	False	[90000, 90000]	Do images binned calibration looking at 120 km	Take WDW 7 images with binned calibration bu 12 sec exposure intervall
2022-11-30 18:00:00	2022-12-01 06:00:00	3103	MODE1	3	92500	True	[]
2022-12-01 11:00:00	2022-12-01 14:30:00	3130	POL	2	92500	False	[]
2022-12-01 11:00:00	2022-12-01 14:30:00	3130	POL	2	92500	False	[]
2022-12-01 11:00:00	2022-12-01 14:30:00	3130	POL	1	92500	False	[]
2022-12-01 18:00:00	2022-12-02 00:00:00	3103	MODE1	4	92500	False	[]
2022-12-01 18:00:00	2022-12-02 00:00:00	3103	MODE1	3	92500	False	[]
2022-12-02 04:00:00	2022-12-02 05:00:00	3120	CROP	1	92500	False	[]
2022-12-02 11:00:00	2022-12-02 13:00:00	3110	NADLMB	2	92500	False	[]	Moon measurement from all channels	Start with limb pointing at 90 km and follow star for 4 minutes. Take full frame images with all channels with TBD inttime
2022-12-02 11:00:00	2022-12-02 13:00:00	3110	NADLMB	1	92500	False	[]	Moon measurement from all channels	Start with limb pointing at 90 km and follow star for 4 minutes. Take full frame images with all channels with TBD inttime
2022-12-02 20:00:00	2022-12-02 21:30:00	3160	ODIN1	1	90000	False	[]	Moon measurement from all channels	Start with limb pointing at 90 km and follow star for 4 minutes. Take full frame images with all channels with TBD inttime
2022-12-02 23:00:00	2022-12-03 00:30:00	3161	ODIN2	1	90000	False	[]	Moon measurement from all channels	Start with limb pointing at 90 km and follow star for 4 minutes. Take full frame images with all channels with TBD inttime
2022-12-03 12:00:00	2022-12-04 00:00:00	3104	MODE5	1	92500	False	[]	Moon measurement from all channels	Start with limb pointing at 90 km and follow star for 4 minutes. Take full frame images with all channels with TBD inttime
2022-12-04 12:00:00	2022-12-05 00:00:00	3104	MODE1y	1	92500	True	[]	Do 2 fullframe images looking at NP km with all limb channels, do 2*1s 2*2 s etc	Pitch down 5 degrees and yaw away from sun and take dark images in all limb channels with 1,3, 5, 10, 15 and 30 s
2022-12-05 06:00:00	2022-12-05 18:00:00	3105	MODE1y	1	92500	True	[]	Redo operational mode 1 with possible bug fixes	TBD

								Add yaw to operational mode	TBD
								Redo star pointing with single integration time for all channels	Start with limb pointing at 90 km and follow star for 4 minutes. Take full frame images with all channels with TBD inttime

								Do binned calibration
								Redo operational mode 1 with possible bug fixes	TBD

								Fullframe images	Look at limb with nadir at altitude 60 km and 90 km fullframe inttime 1,5 and 10, 20 and 30 s
								Fullframe images	Look at limb with nadir at altitude 120 and 150 km fullframe inttime 1,5 and 10, 20 and 30 s
								Fullframe images	Look at limb with nadir at altitude 190 and 230 km fullframe inttime 1,5 and 10, 20 and 30 s
								Fullframe images	Look at limb with nadir at altitude 170 km and 230 km fullframe inttime 1,5 and 10, 20 and 30 s
								Binned images	Look at limb with nadir at altitude 170 km and 230 km binned inttime 1,5 and 10, 20 and 30 s